## Slide 1
SellerPortal Consignment
CI/CD Migration POC
GitHub Actions · ArgoCD · Kubernetes on EKS
Sandbox POC | 2-3 Week Migration | Zero-Downtime

## Slide 2
Agenda
01
Current State & Pain Points
Jenkins + Octopus today
02
Target Architecture
GitHub Actions + ArgoCD + EKS
03
Phase A — S3/CloudFront
Drop-in Jenkins replacement (Week 1)
04
Phase B — Kubernetes
Containerise & deploy to EKS (Week 2-3)
05
POC Sandbox Walkthrough
Live demo flow
06
Secrets & Environments
GitHub + ArgoCD config
07
Risk Mitigation & Rollback
How we stay safe
08
Timeline & Success Metrics
Definition of done

## Slide 3
Current State — Pain Points
Jenkins Sequential Builds
One env at a time — slow, fragile pipelines
Octopus Deploy
Manual approvals, complex runbooks
Static S3/CloudFront
No container story, hard to scale
Cross-account IAM complexity
Secrets scattered across tools
Current Metrics
15–20 min
Build time (sequential)
4 accounts
Manual Octopus steps per env
~0
Automated rollback support
16
Secrets to manage manually

## Slide 4
Target Architecture — End State
Git Push
/ PR
GitHub
Actions CI
Docker
+ ECR
ArgoCD
GitOps
EKS
Cluster
Phase A: GitHub Actions + S3 (Week 1)
Phase B: Kubernetes + ArgoCD (Week 2-3)
4 Environments
dev · qa · staging · production
IAM OIDC per account
GitOps Flow
Git = source of truth
ArgoCD auto-sync dev/qa
Manual approval staging/prod
Zero Downtime
Rolling updates
HPA + health probes
ArgoCD instant rollback

## Slide 5
Phase A — GitHub Actions + S3/CloudFront (Week 1)
1
Merge feature branch
feature/github-actions-deployment
8 commits ahead of main, ready to merge
2
Configure 16 Secrets
AWS roles, S3 buckets, CF IDs
Slack webhooks — see SECRETS_CONFIGURATION.md
3
Set GitHub Environments
dev/qa: auto-deploy on push
staging/prod: required reviewer approval
4
AWS OIDC Trust Policies
Update IAM trust in all 4 accounts
Allow github.com/TCGplayer/sellerportal-consignment
5
Parallel Run 3-5 days
Jenkins/Octopus stays active
Compare outputs, verify parity
6
Cutover
Disable Jenkins jobs
GitHub Actions becomes sole pipeline

## Slide 6
Phase B — Kubernetes + ArgoCD (Week 2–3)
Push to main
Docker build
Push to ECR
ArgoCD sync
EKS deploy
Dockerfile
Multi-stage build
Node 20 builder + nginx alpine
Health endpoint /health
K8s Manifests (base)
Deployment + Service
Ingress + ConfigMap
Kustomize base layer
4 Env Overlays
dev/qa/stg/prd patches
Replica, ingress, configmap
HPA for stg + prd
ArgoCD Applications
application-{env}.yaml
Auto-sync: dev, qa
Manual: staging, production
build.yml update
Add Docker build steps
ECR login + push
Kustomize tag update + git commit
argocd-sync.yml
Manual sync workflow
Sync or rollback action
Approval gate per env

## Slide 7
POC Sandbox — Demo Walkthrough
1
Create ECR Repo
aws ecr create-repository \
--repository-name sellerportal-consignment \
--image-scanning-configuration scanOnPush=true
2
Apply ArgoCD App (dev)
kubectl apply \
-f k8s/argocd/application-dev.yaml \
-n argocd
3
Trigger GitHub Actions
git push origin main
# build.yml runs automatically
# Builds Docker → pushes ECR → updates kustomize
4
Watch ArgoCD Sync
argocd app get \
sellerportal-consignment-dev
# Auto-sync detects new image tag in git
5
Verify Deployment
kubectl get pods -n sellerportal-consignment
curl https://consignment.dev.tcgplayer.com/health
# Expect: healthy
6
Test Rollback
# In GitHub Actions UI:
# Trigger argocd-sync.yml
# environment=dev action=rollback

## Slide 8
GitHub Secrets & Environments Setup
Environment
Trigger
Approval
Secrets Scope
dev
Push to main
None
AWS_ROLE_ARN_DEV, S3_BUCKET_dev, CF_DIST_dev
qa
Push to main
None
AWS_ROLE_ARN_QA, S3_BUCKET_qa, CF_DIST_qa
staging
workflow_dispatch
1 reviewer
AWS_ROLE_ARN_STG, S3_BUCKET_stg, CF_DIST_stg
production
workflow_dispatch
2 reviewers
AWS_ROLE_ARN_PRD, S3_BUCKET_prd, CF_DIST_prd
Additional Secrets for Phase B (ArgoCD)
ARGOCD_SERVER
ArgoCD server hostname (per env or shared)
ARGOCD_AUTH_TOKEN
ArgoCD service account token
FONTAWESOME_AUTHTOKEN
FontAwesome Pro npm token (build-time)
NPM_TOKEN
Private npm registry token (if needed)

## Slide 9
Risk Mitigation & Rollback Strategy
HIGH
Risk: Micro-frontend breaks in shell
✓ CORS tested in dev first · Verify import-map URL before cutover
↩ Revert shell import-map → S3/CloudFront URL
HIGH
Risk: Production outage during cutover
✓ Parallel run 24-48h (S3 + K8s active) · Phased import-map update
↩ Shell import-map back to S3 · ArgoCD rollback or kubectl rollout undo
MEDIUM
Risk: Docker build failure in CI
✓ Test Dockerfile locally before push · Clear build arg error messages
↩ Iterate Dockerfile — S3 path still works
MEDIUM
Risk: ArgoCD sync failure
✓ kubectl apply --dry-run in CI · Validate manifests with kustomize build
↩ Fix manifest YAML, re-sync
LOW
Risk: Performance regression vs CloudFront
✓ Load test staging (ab/k6) · HPA configured, resources right-sized
↩ DNS/import-map back to CloudFront
LOW
Risk: Increased AWS costs
✓ 50m/200m CPU, 64Mi/128Mi mem limits · HPA only scales under load
↩ Adjust resource limits, monitor Cost Explorer

## Slide 10
Timeline & Success Metrics
Week 1
Merge feature branch
Config 16 secrets
OIDC trust policies
Dev/QA auto-deploy
Parallel run w/ Jenkins
Week 2
K8s manifests + Dockerfile
Create ECR repos
Local Docker testing
Deploy to dev
Update dev shell import-map
Week 3
QA deploy + regression
Staging load test
Practice rollback
Production deployment
Decommission S3 (after 48h)
< 10 min
Deploy time
< 5 min
Rollback time
> 95%
Deploy success rate
0
Downtime (rolling updates)

## Slide 11
Ready to Run the POC
Immediate next steps to get started
1
Review & approve this plan with stakeholders
2
Confirm EKS endpoints, ArgoCD URLs, ACM cert ARNs
3
Configure 16 GitHub Secrets + 4 Environments
4
Update AWS OIDC trust policies in all 4 accounts
5
Merge feature/github-actions-deployment → main
6
Create ECR repos & kick off Phase B sandbox